## Sheet1
Project Planner | [5 empty] | Hours spent per month
Hours spent per month
Task | Hours Estimated for Task | Deadline (date) | Hours Spent (calculated) | (Over)/ Under budget | Cumulative Hours | Jun '18 | Jul '18 | Aug '18 | Sep '18 | Oct '18 | Nov '18 | Dec '18 | Jan '19 | Feb '19 | Mar '19 | Apr '19 | May '19 | Notes
Create Website | 1 | 2019-06-05 | 1 | 0 |  | 1
Learn Linear Algebra | 20 | 2019-07-01 | 10 | 0 |  |  | 10
Make Perlin noise | 6 | 2019-09-01 | 5 | 0 |  |  |  | 5
Make Object Heirarchies | 5 | 2019-09-01 | 8 | 0 |  |  | 2 | 6
Implement rendering software | 40 | 2019-09-01 | 40 | 0 |  | 10 | 20 | 10
Blogs | 6 | 2019-09-01 | 5 | 0 |  | 2 | 2 | 2
Combine parts of project | 20 | 2019-09-01 | 35 | 0 |  |  | 5 | 30
Set up LWJGL and intelliJ | 1 | 2019-07-01 | 10 | 0 |  | 10
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTALS | 99 |  | 114 | 0